## Work Assigned Gantt Chart
Entire Team |  |  | Figure 1: Project Gantt Chart
Pragat Wagle
Mark Green
Sahil Dhingra |  |  | Chart describes project tasks and responsibilities for each Phase. Within each phase is an approximate order of operations for completing the tasks, and role assignments where determined.
Kunal Singh
Unassigned
| Phase 1 Project Description and Proposal Due: 11/15/2022 |  |  | Phase 2 EDA and Baseline Pipeline Due: 11/29/2022 |  |  | Phase 3 Feature Selection and Model Tuning Due: 12/6/2022 |  |  | Phase 4 Neural Network and Final Report Due: 12/13/2022
Tasks | Initial | Middle | Final | Initial | Middle | Final | Initial | Middle | Final | Initial | Middle | Final
Project Abstract
Introduction
Project Execution Plan | [13 empty] | Phase 2 Technical Steps
Data Description
Machine Learning Algorithms | [13 empty] | SUMMARIZE (ohe, min/max/sum/var/mean) | STEP | WHO
Machine Learning Pipelines | [12 empty] | ok | Bureau_balance | 1 | MG
Jupyter Notebook Baseline Modeling | [12 empty] | ok | Bureau + Bureau_balance | 3 | MG
Conclusion | [12 empty] | ok | POS_CASH_balance | 1 | SD
Phase Leader Plan | [13 empty] | installments_payments | 1 | KS
Credit Assignment Plan | [13 empty] | credit_card_balance | 1 | PW
Overall proposal appearance | [13 empty] | previous_applications + POS_CASH + installments + credit_card | 3 | SD
Video and in class presentation
Team and Plan updates | [13 empty] | ROLLUP (Left Join into parent table)
Abstract | [12 empty] | ok | Bureau_balance → Bureau | 2 | MG
Project Description (data and tasks) | [13 empty] | POS_CASH_balance -> previous_applications | 2 | SD
EDA | [13 empty] | installments_payments -> previous_applications | 2 | KS
Visual EDA | [13 empty] | credit_card_balance -> previous_applications | 2 | PW
Feature Engineering | [13 empty] | previous_applications → application_test_train | 4 | SD
Building/Running Baseline Model | [13 empty] | bureau → application_test_train | 4 | MG
Results and discussion of results
Conclusion | [13 empty] | EDA / VISUAL EDA (describe, visual matrix)
TBD | [13 empty] | bureau | 5 | MG
TBD | [13 empty] | bureau_balance | 5 | MG
TBD | [13 empty] | previous_applications | 5 | SD
TBD | [13 empty] | POS_CASH_balance | 5 | SD
TBD | [13 empty] | installments_payments | 5 | KS
TBD | [13 empty] | credit_card_balance | 5 | PW
[14 empty] | FEATURE SELECTION ROUND 1 via Colinearity/Correlation contest | 6 | ?
EDA / Visual EDA
[14 empty] | application_test_train - rolled up | 7 | ?
MODEL RUNNING
[14 empty] | run baseline LR model on application_test_train (rolled up and feature selected) | 8 | ?